## Plan Progress as of 05092012
Task | Responsible | Start | End | Days | Complete | time axis 2014-01-28 to 2014-05-04
 | time axis 2014-01-28 to 2014-05-04
Planning | (Nathan)
Team Poster | Team | 2014-01-28 | 2014-02-04 | 6 | 100% | 6
Schedule client meeting | Team | 2014-02-06 | 2014-02-13 | 6 | 100% | 6
Draft planning document | Team | 2014-02-11 | 2014-02-18 | 6 | 100% | 6
Final Document | Team | 2014-02-18 | 2014-02-20 | 3 | 100% | 3
Summary, Scope, Success | Matthew, Ryan | 2014-02-18 | 2014-02-20 | 3 | 100% | 3
References | Nathan, Isaac | 2014-02-18 | 2014-02-20 | 3 | 100% | 3
Risks | Danielle, Isaac | 2014-02-18 | 2014-02-20 | 3 | 100% | 3
Schedule | Forrest, Nathan | 2014-02-18 | 2014-02-20 | 3 | 100% | 3
Proofread and approve | Team | 2014-02-20 | 2014-02-20 | 1 | 100% | 1
Requirements | (Matthew) |  |  | 0 |  | 0
Fluid UI Mockups | Team | 2014-02-20 | 2014-02-27 | 6 | 100% | 6
Client Approval | Nathan, Isaac, Matt | 2014-02-20 | 2014-02-25 | 4 | 100% | 4
Six-wk project update | Isaac, Matt | 2014-02-20 | 2014-02-27 | 6 | 100% | 6
Requirements Document | Team | 2014-03-04 | 2014-03-27 | 18 | 100% | 3
Sections 1 & 2 (front matter) | Team | 2014-03-04 | 2014-03-08 | 4 | 100% | 0
Section 3 (functional) | Matthew, Forrest | 2014-03-17 | 2014-03-25 | 7 | 100% | 6
S 4 (design) | Isaac | 2014-03-18 | 2014-03-25 | 6 | 100%
S 5 (performance) | Forrest | 2014-03-18 | 2014-03-25 | 6 | 100%
S 6 (other) | Nathan, Danielle | 2014-03-18 | 2014-03-25 | 6 | 100%
S 7 (scenarios) | Nathan, Isaac, Forrest, Matt | 2014-03-19 | 2014-03-25 | 5 | 100%
S 8 (models & diagrams) | Team | 2014-03-22 | 2014-03-27 | 4 | 100%
8.1 Use case | Team | 2014-03-22 | 2014-03-27 | 4 | 100%
S 9 (this schedule) | Matthew | 2014-03-17 | 2014-03-27 | 9 | 100%
S 10 Footnotes | Nathan, Danielle | 2014-03-25 | 2014-03-27 | 3 | 100% | 1
Final Document | Team | 2014-03-25 | 2014-03-27 | 3 | 100% | 9
Design | (Isaac) |  |  | 0 |  | 3
Project System Models | Team | 2014-03-27 | 2014-04-03 | 6 | 100% | 0
in-class update | Isaac | 2014-04-03 | 2014-04-03 | 1 | 100% | 4.5
Draft design document |  | 2014-03-27 | 2014-04-08 | 9 | 100% | 0
Final document |  | 2014-04-08 | 2014-04-10 | 3 | 100% | 0
Implementation | (Forrest) |  |  | 0 |  | 5.6
Write the app |  | 2014-04-10 | 2014-04-22 | 9 | 50% | 0
in-class update | Forrest | 2014-04-17 | 2014-04-17 | 1 | 0% | 0
Revise the app |  | 2014-04-22 | 2014-04-29 | 6 | 0%
Write readme |  | 2014-04-10 | 2014-04-29 | 14 | 40%
Final presentation | (Danielle) |  |  |  | 0%
Final presentation | Team | 2014-04-17 | 2014-04-29 | 9 | 0%
Website | Nathan, Forrest |  |  | 0
Upload team poster | Matthew | 2014-02-04 | 2014-02-06 | 3 | 100%
Initial website | Forrest | 2014-02-04 | 2014-02-13 | 8 | 100%
Weekly update | Nathan, Forrest | 2014-02-21 | 2014-02-21 | 1 | 100%
Weekly update | Nathan, Forrest | 2014-02-27 | 2014-02-27 | 1 | 100%
Weekly update | Nathan, Forrest | 2014-03-07 | 2014-03-07 | 1 | 100%
Weekly update | Nathan, Forrest | 2014-03-21 | 2014-03-21 | 1 | 100%
Weekly update | Nathan, Forrest | 2014-03-28 | 2014-03-28 | 1 | 100%
Weekly update | Nathan, Forrest | 2014-04-04 | 2014-04-04 | 1 | 100%
Weekly update | Nathan, Forrest | 2014-04-11 | 2014-04-11 | 1 | 100%
Weekly update | Nathan, Forrest | 2014-04-18 | 2014-04-18 | 1 | 50%
Weekly update | Nathan, Forrest | 2014-04-25 | 2014-04-25 | 1 | 0%
0
|  |  |  | 203 | 40.44%
Today's Date | 2014-04-15 16:10 | 0%
Start Date | 2014-01-28
Projected End Date | 2014-04-29
Total Man Days | 203
Project Duration | 91
RU ITEC Agenda - Project Tracking

## Sheet2
Nonworking Date | Reason
2012-05-21 | MetLife Holiday
2012-05-22 | MetLife Holiday
2012-05-23 | MetLife Holiday
2012-05-24 | MetLife Holiday
2012-05-25 | MetLife Holiday
2012-05-28 | Memorial Day

## Sheet3
Legend
| Active Tasks | Tasks Overdue Start
| Completed Tasks (100%) | Tasks Running Late
| Non-Working Day | Non-Working Day
| Current Day | Current Day
Beyond Projected Last Day